## Slide 1: Project Demo & Progress Update
G7T8 – 888
Project Manager: Hani ‘Aiman
Group Members: Andy, Daniel, Hong Yuan, Xu Ying

## Slide 2: Agenda
Functionalities
Schedule: Where are we now?
Metrics
Pair Programming
Lessons Learnt

## Slide 3: Functionalities
We are not planning to drop or add any functionalities
Functionalities
Schedule
Metrics
Pair Programming
Lessons Learnt

## Slide 4: Schedule: Where are we now?
3
4
5
6
7
8
Iteration 1
Iteration 2
Iteration 3
PM: Andy
Log-in GUI page
User GUI page
Admin GUI pager
PM: Daniel
Log-in function
Location GUI page
Breakdown & Top-K report function
PM: Xu Ying
Heatmap GUI page
Bootstrap GUI & function
Top-K companion & Top-K next function
Automatic group identification GUI
Functionalities
Schedule
Metrics
Pair Programming
Lessons Learnt

## Slide 5: Schedule: Where are we now?
9
10
11
12
13
14
Iteration 4
Iteration 5
Iteration 6
PM: Hani
JSON & web service
Automatic group identification function
Improve UI & debug functions
PM: Hong Yuan
Improve UI
PM: Andy
Finalize report
Functionalities
Schedule
Metrics
Pair Programming
Lessons Learnt

## Slide 6: Milestone
Iteration 3
PM: Xu Ying
PM Review
PM: Hani
Project Demo & Update
PM: Hong Yuan
UAT
7
8
9
10
11
12
14
13
Iteration 4
Iteration 5
Iteration 6
PM: Andy
Final Presentation
Functionalities
Schedule
Metrics
Pair Programming
Lessons Learnt

## Slide 7: Critical Path – Iteration 1
Functionalities
Schedule
Metrics
Pair Programming
Lessons Learnt
Diagram designing (2 days)
Project analysis & planning
(1 day)
Login & User Page GUI
(2 days)
Admin Page GUI
(2 days)

## Slide 8: Critical Path – Iteration 2
Functionalities
Schedule
Metrics
Pair Programming
Lessons Learnt
Database
(1 day)
Basic Location Report GUI
(1 day)
Login Functionality
(1 day)
Breakdown Functionality
(3 days)
Top-K Popular Place Functionality
(3 days)
Integration
(1 day)

## Slide 9: Critical Path – Iteration 3
Functionalities
Schedule
Metrics
Pair Programming
Lessons Learnt
Diagram designing
(1 day)
Bootstrap GUI
(1 day)
Heatmap Functionality
(2 days)
Bootstrap Functionality
(4 days)
Top-K Companion Functionality
(1 day)
Automatic Group Identification GUI
(1 day)
Heatmap GUI
(1 day)
Top-K Next Functionality
(1 day)
Integration & Testing of integration
(4 days)
Slack
(1 day)

## Slide 10: Critical Path – Iteration 4
Functionalities
Schedule
Metrics
Pair Programming
Lessons Learnt
JSON & web services
(3 days)
Improve UI & functionalities
(2 days)
Automatic Group Identification functionality
(3 day)
Debug & Testing of UI & functionalities
(4 days)

## Slide 11: Critical Path – Iteration 5
Functionalities
Schedule
Metrics
Pair Programming
Lessons Learnt
UAT Presentation Preparation
Debug & Test functionalities
(4 days)
UAT Presentation

## Slide 12: Critical Path – Iteration 6
Functionalities
Schedule
Metrics
Pair Programming
Lessons Learnt
Final Presentation Preparation
Finalize Project
(4 days)
Final Presentation

## Slide 13: Task Metrics
Functionalities
Schedule
Metrics
Pair Programming
Lessons Learnt
Iteration | Planned Task | Completed Task | Task Metrics
1 | 7 | 7 | 1
2 | 19 | 19 | 1
3 | 48 | 48 | 0.84210
4 | 33 | 20 | 0.6061

## Slide 14: Task Metrics: Mitigation Plan for Iteration 3
Functionalities
Schedule
Metrics
Pair Programming
Lessons Learnt
Our team re-estimated the tasks for the future iterations. We deducted 2 days from our buffer days.

## Slide 15: Bug Metrics
Functionalities
Schedule
Metrics
Pair Programming
Lessons Learnt
Current bug metric score:
We have solved all the bugs found in testing, using our planned debugging time in the iteration

## Slide 16: Pair Programming
Iteration | Milestone | Project Manager | Pair Programmer 1 | Pair Programmer 2
4 | Project Demo & Progress Update | Hani | Daniel Xu Ying | Andy Hong Yuan
5 | UAT | Hong Yuan | Daniel Hani | Andy Xu Ying
Functionalities
Schedule
Metrics
Pair Programming
Lessons Learnt

## Slide 17: Pair Programming
Iteration | Functionalities | Tasks | Andy | Daniel | Hani | Hong Yuan | Xu Ying
3 | Heatmap |  | ✔ |  | ✔ |  | 
 | Bootstrap | Upload |  | ✔ |  | ✔ | 
 |  | Delete |  | ✔ |  | ✔ | 
 | Basic Location Report | Top-K companion | ✔ |  | ✔ |  | 
 |  | Top-K next place | ✔ |  | ✔ |  | 
4 | JSON & Web services |  | ✔ |  |  | ✔ | 
 | Automatic group identification |  |  | ✔ |  |  | ✔
Functionalities
Schedule
Metrics
Pair Programming
Lessons Learnt
Note: Iteration 5 Pair Programming timings are used for debugging and testing

## Slide 18: Lessons Learnt
Functionalities
Schedule
Metrics
Pair Programming
Lessons Learnt
Bug metrics and test cases should be as detailed and specific as possible
Indicate additional tasks as unplanned task during a current iteration
More paired programming hours should be allocated to each pair programming, depending on the task
Team reflection and sharing is needed for each iteration to continue improving project management as a team

## Slide 19: Thank you
Question & Answer