## Sheet1
S/N | Functionality | Description | Test Inputs | Test Procedure | Expected Results | Iteration 1 |  | Iteration 2 |  | Iteration 3 |  | Iteration 4 |  | Iteration 5 |  | Iteration 6
[6 empty] | Actual Results | Pass/Fail | Actual Results | Pass/Fail | Actual Results | Pass/Fail | Actual Results | Pass/Fail | Actual Results | Pass/Fail | Actual Results | Pass/Fail
1 | Login | Validate that user with correct credential can login | Username: zorro.fan.2010 Password: zxcvbn1284 | Put username into username input field and password into password input field. Submit | Login succeed. The home page is displayed | Login succeed. The home page is displayed | Pass | Login succeed. The home page is displayed | Pass | Login succeed. The home page is displayed | Pass
2 | Login | User should not be able to access the website without entering any username and/or password | Username: Password: Username zorro.fan.2010 Password: Username: Password zxcvbn1284 | Submit without entering username and/or password | Invalid login. Pop up required fill | Invalid login. Pop up required fill | Pass | Invalid login. Pop up required fill | Pass | Invalid login. Pop up required fill | Pass
3 | Login | User/non-user should not be able to access admin page via URL. Admin/non-user should not be able to access user page via URL | adminPage.jsp userPage.jsp | Type the inputs into URL. Enter | Return user/admin back to their respective accessible website. Return non-user back to login page | User/non-user can access admin page via URL, admin/non-user can access user page via URL. No error messages | Fail | Return user/admin back to their respective accessible website. Return non-user back to login page | Pass | Return user/admin back to their respective accessible website. Return non-user back to login page | Pass
4 | Login | SQL injection | Username: abc OR 1=1 Password: abc OR 1=1 | Put username into username input field and password into password input field. Submit | Invalid login. Error message: "Invalid login" |  |  | Invalid login. Error message: "Invalid login" | Pass | Invalid login. Error message: "Invalid login" | Pass
5 | Login | User should not be able to access the website with special symbols as username | Username: % Password: zxcvbn1284 | Put username into username input field and password into password input field. Submit | Invalid login. Error message: "Invalid login" |  |  | User page can be accessed by inputting "%" in the username and the correct password. No error message | Fail | Invalid login. Error message: "Invalid login" | Pass
6 | Login | After logging out, user should not be allowed back into the website by clicking the back button | nil | Logout. Click back button | Return back to login page |  |  | After the user log outs, user is still able to return to the page by clicking the back button. No error message | Fail | Return back to login page | Pass
7 | Basic Location Report (Breakdown) | Accuracy for calculation results for breakdown report must be tallied to SQL query | Date: 2017-02-06 11:00:00 Sort by Year, gender | Put date into date input field and click year, gender. Submit | 4 columns are generated (Year, Gender, Qty, Percentage). 10 rows are generated. Sum of the percentages add up to 100% +-1% and sum of qty tally with the total |  |  | Breakdown by year and gender but unable to get the last 15 minutes of the user input time hence the percentage doesn't add up | Fail | 4 columns are generated (Year, Gender, Qty, Percentage). 10 rows are generated. Sum of the percentages add up to 100% +-1% and sum of qty tally with the total | Pass
8 | Basic Location Report (Popular) | TopK popular places report should display semantic places with the same no of pax into 1 row and no ranking should be skipped | Date: 2017-02-06 11:00:00 TopK: 3 | Put date into date input field and click TopK | 3 columns are generated (Rank, Semantic Place, No of Pax). Rows equal to the topK selected. Semantic places with the same no of pax are combined into a single row, no rankings are skipped and semantic places are not IDs |  |  | TopK popular places displays multiple rows of semantic places when the number of pax is the same | Fail | 3 columns are generated (Rank, Semantic Place, No of Pax). Rows equal to the topK selected. Semantic places with the same no of pax are combined into a single row, no rankings are skipped and semantic places are not IDs | Fail
9 | Basic Location Report (Breakdown) | User should not be able to submit without entering a date in the breakdown report | Date: Sort by Year | Submit without entering date | Invalid submit. Pop up required fill |  |  |  |  | Invalid submit. Pop up required fill | Pass
10 | Basic Location Report (Breakdown) | Breakdown report should not be generated when user input the same sorting category | Date: Sort by Year, Year, Year | Put date into date input field and sort by year, year, year. Submit | Invalid submit. Error message: "Report generation failed, duplicated option found: year" |  |  |  |  | Invalid submit. Error message: "Report generation failed, duplicated option found: year" | Pass
11 | Basic Location Report (Breakdown) | Breakdown report should not be generated when user input wrong date format | Date: 2017-02-99 11:00:00 Sort by Year Date: 9999-02-06 11:00:00 Sort by Year Date: 2017-99-06 99:00:00 Sort by Year Date: 2017-02-99 11:99:00 Sort by Year Date: 2017-02-99 11:00:99 Sort by Year Date: 2017-02-99 11:00:00 Sort by Year | Put date into date input field and sort by year. Submit | Invalid submit. Error message: "Data not available within the date" |  |  |  |  | The table still generates but no values are inside when user enter wrong date format. No error message | Fail
12 | Basic Location Report (Popular) | User should not be able to submit without entering a date in the topK popular places report | Date: TopK: 3 | Put date into date input field and choose TopK | Invalid submit. Pop up required fill |  |  |  |  | Invalid submit. Pop up required fill | Pass
13 | Basic Location Report (Popular) | TopK popular places report should not be generated when user input wrong date format | Date: 2017-02-99 11:00:00 TopK: 3 Date: 9999-02-06 11:00:00 TopK: 3 Date: 2017-99-06 99:00:00 TopK: 3 Date: 2017-02-99 11:99:00 TopK: 3 Date: 2017-02-99 11:00:99 TopK: 3 Date: 2017-02-99 11:00:00 TopK: 3 | Put date into date input field and choose TopK | Invalid submit. Error message: "Data not available within the date" |  |  |  |  | The table still generates but no values are inside when user enter wrong date format. No error message | Fail
14 | Basic Location Report (Companion) | TopK companions report should display macaddresses with the same co-located time into 1 row and no ranking should be skipped | Date: 2017-02-06 11:00:00 Macaddress: 0204de726084ed19c3c269f2636a91a341167f7c TopK: 3 | Put date into date input, macaddress into macaddress input and choose TopK | 3 columns are generated (Rank, Macaddress, Co-Located Time (in seconds)). Rows equals to the topK selected. Macaddresses with the same co-located time are combined into 1 row, no rankings are skipped and co-located time is not more than 900 seconds (15 minutes) |  |  |  |  | 3 columns are generated (Rank, Macaddress, Co-Located Time (in seconds)). Rows equals to the topK selected. Macaddresses with the same co-located time are combined into 1 row, no rankings are skipped and co-located time is not more than 900 seconds (15 minutes) | Pass
15 | Basic Location Report (Companion) | User should not be able to submit without entering a date and/or macaddress in the topK companions report | Date: Macaddress: 0204de726084ed19c3c269f2636a91a341167f7c TopK: 3 Date: 2017-02-06 11:00:00 Macaddress: TopK: 3 Date: Macaddress: TopK: 3 | Put date into date input, macaddress into macaddress input and choose TopK | Invalid submit. Pop up required fill |  |  |  |  | Invalid submit. Pop up required fill | Pass
16 | Basic Location Report (Companion) | TopK companions report should not be generated when user input wrong date format | Date: 2017-02-99 11:00:00 Macaddress: 0204de726084ed19c3c269f2636a91a341167f7c TopK: 3 Date: 9999-02-06 11:00:00 Macaddress: 0204de726084ed19c3c269f2636a91a341167f7c TopK: 3 Date: 2017-99-06 99:00:00 Macaddress: 0204de726084ed19c3c269f2636a91a341167f7c TopK: 3 Date: 2017-02-99 11:99:00 Macaddress: 0204de726084ed19c3c269f2636a91a341167f7c TopK: 3 Date: 2017-02-99 11:00:99 Macaddress: 0204de726084ed19c3c269f2636a91a341167f7c TopK: 3 Date: 2017-02-99 11:00:00 Macaddress: 0204de726084ed19c3c269f2636a91a341167f7c TopK: 3 | Put date into date input, macaddress into macaddress input and choose TopK | Invalid submit. Error message: "Data not available within the date" |  |  |  |  | The table still generates but no values are inside when user enter wrong date format. No error message | Fail
17 | Basic Location Report (Companion) | TopK companions report should not be generated when user input wrong macaddress | Date: 2017-02-06 11:00:00 Macaddress: hellothisisnotamacaddress TopK: 3 | Put date into date input, macaddress into macaddress input and choose TopK | Invalid submit. Error message: "Data not available for this macaddress" |  |  |  |  | The table still generates but no values are inside when user enter wrong macaddress. No error message | Fail
18 | Basic Location Report (Next Place) | TopK next places report should display semantic places with the same no of pax into 1 row and no ranking should be skipped | Date: 2017-02-06 11:00:00 Location name: SMUSISL2StudyArea1 TopK: 3 | Put date into date input, choose semantic place and choose TopK | First table generates 4 columns (Rank, Semantic Place, No of Pax, % of Users Visiting this Semantic Place). Rows equals to the topK selected. Semantic places with the same no of pax are combined into 1 row, no rankings are skipped. No of pax divided by second table's no of pax in semantic place queried * 100 is equal to the % of users visiting that semantic place Second table generates 3 columns (Semantic place queried, No of Pax in Semantic Place Queried, No of Pax who Visited Next Semantic Place). No of pax who visited next semantic place excludes those who left the place but have not visited another place and those still staying in the semantic place queried. |  |  |  |  | First table generates 4 columns (Rank, Semantic Place, No of Pax, % of Users Visiting this Semantic Place). Rows equals to the topK selected. Semantic places with the same no of pax are combined into 1 row, no rankings are skipped. No of pax divided by second table's no of pax in semantic place queried * 100 is equal to the % of users visiting that semantic place Second table generates 3 columns (Semantic place queried, No of Pax in Semantic Place Queried, No of Pax who Visited Next Semantic Place). No of pax who visited next semantic place excludes those who left the place but have not visited another place and those still staying in the semantic place queried. | Pass
19 | Basic Location Report (Next Place) | User should not be able to submit without entering a date in the topK next places report | Date: Location name: SMUSISL2StudyArea1 TopK: 3 | Put date into date input, choose semantic place and choose TopK | Invalid submit. Pop up required fill |  |  |  |  | Invalid submit. Pop up required fill | Pass
20 | Basic Location Report (Next Place) | TopK next places report should not be generated when user input wrong date format | Date: 2017-02-99 11:00:00 Location name: SMUSISL2StudyArea1 TopK: 3 Date: 9999-02-06 11:00:00 Location name: SMUSISL2StudyArea1 TopK: 3 Date: 2017-99-06 99:00:00 Location name: SMUSISL2StudyArea1 TopK: 3 Date: 2017-02-99 11:99:00 Location name: SMUSISL2StudyArea1 TopK: 3 Date: 2017-02-99 11:00:99 Location name: SMUSISL2StudyArea1 TopK: 3 Date: 2017-02-99 11:00:00 Location name: SMUSISL2StudyArea1 TopK: 3 | Put date into date input, choose semantic place and choose TopK | Invalid submit. Error message: "Data not available within the date" |  |  |  |  | The table still generates but no values are inside when user enter wrong date format. No error message | Fail
21 | Heatmap | Heatmap should display table and a heatmap picture with the respective heat levels colors | Date: 2017-02-06 11:00:00 Level: 3 | Put date into date input and choose level | 3 columns are generated (Semantic Place, Quantity, Heat Level). Quantity <= 0 have a heat level of 0, quantity <= 2 have a heat level of 1, quantity <= 5 have a heat level of 2, quantity <= 10 have a heat level of 3, quantity <= 20 have a heat level of 4, quantity <= 30 have a heat level of 5, quantity>30 have a heat level of 6. Heatmap picture is generated according to the heat levels and semantic places in the table (light yellow color,0 to brightest red, 6) |  |  |  |  | 3 columns are generated (Semantic Place, Quantity, Heat Level). Quantity <= 0 have a heat level of 0, quantity <= 2 have a heat level of 1, quantity <= 5 have a heat level of 2, quantity <= 10 have a heat level of 3, quantity <= 20 have a heat level of 4, quantity <= 30 have a heat level of 5, quantity>30 have a heat level of 6. Heatmap picture is generated according to the heat levels and semantic places in the table (light yellow color,0 to brightest red, 6) | Pass
22 | Heatmap | User should not be able to submit without entering a date in the heatmap | Date: Level: 3 | Put date into date input and choose level | Invalid submit. Pop up required fill |  |  |  |  | Invalid submit. Pop up required fill | Pass
23 | Heatmap | Heatmap should not be generated when user input wrong date format | Date: 2017-02-99 11:00:00 Level: 3 Date: 9999-02-06 11:00:00 Level: 3 Date: 2017-99-06 99:00:00 Level: 3 Date: 2017-02-99 11:99:00 Level: 3 Date: 2017-02-99 11:00:99 Level: 3 Date: 2017-02-99 11:00:00 Level: 3 | Put date into date input and choose level | Invalid submit. Error message: "Data not available within the date" |  |  |  |  | The table still generates but no values are inside and heatmap picture still generates but with no values when user enter wrong date format. No error message | Fail
24 | Bootstrap (Initialize) | Clear the database and upload new data | data.zip (with 3 files, location.csv, location-lookup.csv, demographics.csv) | Select the file and click upload button | PhpMyAdmin clears the respective tables and insert the data accordingly. Data does not have any leading and trailing whitespaces. Data validations adhere to the requirements stated and display error message of all invalid rows. Duplicates checking is done for location.csv, the latest row is loaded into the database and the previous row(s) is discarded and display error message of all the duplicated rows. If no error, success message displayed |  |  |  |  | PhpMyAdmin clears the respective tables and insert the data accordingly. Data does not have any leading and trailing whitespaces. Data validations adhere to the requirements stated and display error message of all invalid rows. Duplicates checking is done for location.csv, the latest row is loaded into the database and the previous row(s) is discarded and display error message of all the duplicated rows. If no error, success message displayed | Pass
25 | Bootstrap (Initialize) | User should not be able to upload nothing into the database from initialize file upload | nil | Select no file and click upload button | Invalid upload. Error message: "No files uploaded" |  |  |  |  | Invalid upload. Error message: "No files uploaded" | Pass
26 | Bootstrap (Additional) | Validate that duplicated rows in the files and database. Discard the duplicate one in the additional file uploaded | data.zip (with 2 files, location.csv, demographics.csv) | Select the file and click upload button | Insert the data accordingly into PhpMyAdmin. Data does not have any leading and trailing whitespaces. Data validations adhere to the requirements stated and display error message of all invalid rows. Duplicates checking is done for location.csv, the latest row is loaded into the database and the previous row(s) is discarded and display error message of all the duplicated rows. Duplicates checking is done between files and database, discard the duplicate one in the file uploaded and display error message of all the duplicated rows. If no error, success message displayed |  |  |  |  | Insert the data accordingly into PhpMyAdmin. Data does not have any leading and trailing whitespaces. Data validations adhere to the requirements stated and display error message of all invalid rows. Duplicates checking is done for location.csv, the latest row is loaded into the database and the previous row(s) is discarded and display error message of all the duplicated rows. Duplicates checking is done between files and database, discard the duplicate one in the file uploaded and display error message of all the duplicated rows. If no error, success message displayed | Pass
27 | Bootstrap (Additional) | User should not be able to upload nothing into the database from additonal file upload | nil | Select no file and click upload button | Invalid upload. Error message: "No files uploaded" |  |  |  |  | Invalid upload. Error message: "No files uploaded" | Pass
28
29
30
31